## 2010 Budget
2010 RTF Workplan & Budget | [5 empty] | 5-Year Projection | [7 empty] | Related 6th Plan Action Items
Work Description |  | Completion Date | CY 2010 Budget | CY 2010 Subtotal |  | CY 2010 Budget | Notes on Out-Year Projections | CY 2011 Budget | CY 2012 Budget | CY 2013 Budget | CY 2014 Budget | 5-Year Budget Total | 5-Year Subtotal
New Projects | End-Use Load Study - Phase 2a. With Phase 1 complete (as of Sept 2009), subcommittee will make a recommendation on next steps, which could include: a) putting together a data warehouse, b) performing the first round of studies (either meta, field data collection, or c) other. | 2010 | 150000 | 750000 |  | 150000 | Ongoing data collection, warehouse maintenance, and out-of-Region collaboration efforts. Steady funding would allow for large-scale muli-year projects and/or small and medium projects as needed. | 500000 | 500000 | 500000 | 500000 | 2150000 | 3540000 | CONS-21
| Review RTF measures against others': Compare RTF's list of deemed measures with Energy Star and CEE specifications. Add missing measures. Review energy savings methodologies from other utilities and entities around the Region and the country. Understand the differences to come up with the best approach. Parties outside the Region may be interested in supporting this work. (SOW in 2009) | 2010 | 200000 |  |  | 200000 | Continuing collaboration and updates, with both in-Region and out-of-Region entities. | 50000 | 50000 | 50000 | 50000 | 400000 |  | CONS-10
| Provide Direction for Measure Life. Provide the Region with better direction for determining measure life. Literature review of measure life & recommendations on ongoing methodology. (SOW in 2009) | 2010 | 50000 |  |  | 50000 | Assumes continuing implementation of the measure life methodology for new measures and revisions of measure lives for existing measures as new data become available. | 10000 | 10000 | 10000 | 10000 | 90000 |  | CONS-10
| Simplified M&V protocols and/or calculators for non-deemable measures, including behavioral and O&M measures: Develop streamlined field test protocols and M&V methods on custom commercial and industrial projects that may need some kind of modeling. Also, develop protocols for M&V and a better understanding of persistence of savings for behavioral and O&M Measures. The goal is to reduce the burden of M&V while still getting reliable savings estimates. Coordinate implementation, training. Many in the region are currently using various methods - need to reconcile. RTF is likely to issue a contract to catalog what others are doing and harvest the best methods to use going forward. Also, coordination with BPA/Cascade/Cadmus work on Industrial Energy Management and focus some efforts on Comercial HVAC Controls. (SOW in 2009) | 2010 | 300000 |  |  | 300000 | Continued development of protocols for the first few years (higher funding needs), then maintenance and review of existing protocols and calculators and development of new protocols and calculators as needed (lower funding needs). | 130000 | 130000 | 130000 | 80000 | 770000 |  | CONS-9
| Identify Measures and M&V Protocols that are applicable to small and/or rural utilities | 2010 | 50000 | 750000 |  | 50000 | Continued support. | 20000 | 20000 | 20000 | 20000 | 130000 |  | CONS-17
Ongoing Projects | Provide Technical Support to the Ductless Heat Pump Evaluation. The RTF will provide ongoing technical oversight assistance for the DHP Pilot Project evaluation. This involves reviewing evaluation plans and results. (The pilot goal is to install 2500 units in 2009. The RTF currently has "provisionally deemed" savings. 6th plan calls for 235 aMW at 60-70 mills.) | 2011 | 5000 | 412500 |  | 5000 | Ongoing technical support and review of evaluation work. Revision of deemed energy savings and specifications, based on evaluation results. Assistance with 2nd round of evaluation work for multifamily and manufactured home, if applicable. | 30000 | 50000 | 20000 | 20000 | 125000 | 2102500 | CONS-1
| Heat Pump Water Heater Research. RTF to provide technical review and assistance to a lab testing project of HPWH models from major US manufacturers. Coordinate witih BPA, possibly EPRI. | 2010 | 5000 |  |  | 5000 | (Early Years) - Continue support of lab test. Review of test results for determination of deemed (or provisionally deemed ) energy savings. (Later Years) - Review of field demonstration project's evaluation plan and results. Determination of deemed energy savings based field tests. | 30000 | 30000 | 30000 | 30000 | 125000 |  | CONS-1
| Develop consistent methodology for assigning EUIs to commercial buildings | 2010 | 10000 |  |  | 10000 | Continued updating and maintenance of EUI data. Need consistent definitions for EUI's. Share on RTF website. | 20000 | 20000 | 20000 | 20000 | 90000 |  | CONS-21
| Respond to NEET Recommendations for the RTF. RTF subcommittee to review the NEET recommendations pertaining to the RTF and construct a response. PENDING NEEA evaluation. | early 2010 | 5000 |  |  | 5000 | Project to end in 2010. | 0 | 0 | 0 | 0 | 5000 |  | CONS-8 CONS-21
| Support Roof Top HVAC Work - Commercial Economizer Phase 3. Review findings from Phase 2 and determine next steps. Implement impact evaluation protocol across several regional program models. Develop RTF savings methodology. Test NBI protocol. BPA performing a pilot. Plans to develop a deemed calculator approach. | Through 2010 | 37500 |  |  | 37500 | Ongoing evaluation support and refinements to the deemed calculator and assocated specifications. | 60000 | 60000 | 60000 | 20000 | 237500 |  | CONS-1
| Support Development of Savings Methodologies for Rooftop HVAC. | 2010 | 5000 |  |  | 5000 | Continued DOE2 modeling support. | 5000 | 5000 | 0 | 0 | 15000 |  | CONS-1
| RTF Website. Significant refinements to the RTF website, including RFP and ongoing study information, PTCS provider and specifications information, and up-to-date meeting information. | Ongoing | 100000 |  |  | 100000 | Continued support of website. | 50000 | 50000 | 50000 | 50000 | 300000 |  | CONS-8 CONS-21
| PTR Support. Uploading data to the PTR and perform the required QA/QC. Work with BPA and others to develop inputs. Error tracking. | Ongoing | 15000 |  |  | 15000 | Ongoing work. | 15000 | 15000 | 15000 | 15000 | 75000 |  | CONS-19
| Regional Conservation Progress Tracking | Ongoing | 10000 |  |  | 10000 | Ongoing work. | 10000 | 10000 | 10000 | 10000 | 50000 |  | CONS-19
| Measure and Technology Reviews. Ongoing RTF work to review new measures & technologies and revisions/updates to existing measures, including, but not limited to: - Consumer Electronics: review NEEA's deemed savings estimates - Exterior Lighting - DEI and Voltage Optimization: review deemed savings calculator and technical specifications - Grocery Measures: Ongoing review of deemed savings. - New Manufactured Homes - Federal and/or Energy Star appliance standard updates | Ongoing | 200000 |  |  | 200000 | Ongoing work. | 200000 | 200000 | 200000 | 200000 | 1000000 |  | CONS-1
| IT M&V Protocol Review and Adoption Hire a contractor to represent the RTF in developing RTF approved protocols, working with IT industry, BPA, and others. Initial work will determine focus of future work scope: larger server farms, small/medium sized systems, or both. | 2010 | 20000 |  |  | 20000 | Majority of work on 2011. | 60000 | 0 | 0 | 0 | 80000 |  | CONS-1
RTF Support | Member Special Project Support. Subcommittee meetings and assignments. | Ongoing | 35000 | 195000 |  | 35000 | Ongoing work. | 35000 | 35000 | 35000 | 35000 | 175000 | 975000 | CONS-8
| Member RTF Meetings. RTF member meeting attendance. | Ongoing | 65000 |  |  | 65000 | Ongoing work. | 65000 | 65000 | 65000 | 65000 | 325000 |  | CONS-8
| RTF Meetings. (phone, lunches, minutes) | Ongoing | 20000 |  |  | 20000 | Ongoing. | 20000 | 20000 | 20000 | 20000 | 100000 |  | CONS-8
| Contract Management | Ongoing | 50000 |  |  | 50000 | Ongoing work. | 50000 | 50000 | 50000 | 50000 | 250000 |  | CONS-8
| RTF Management Planning, tracking, organizing RTF affairs (meetings, subcommittee meetings, minor projects, special requests and inquiries, budgeting, etc.) | Ongoing | 25000 |  |  | 25000 | Ongoing work. | 25000 | 25000 | 25000 | 25000 | 125000 |  | CONS-8 | FTE | $/FTE (average)
| Council FTE Overall support and management of the RTF, including technical and administrative functions. (Funding from Council's internal budget, not from RTF contributions). |  | 180000 | 180000 | 180000 | 180000 | Ongoing work. | 180000 | 180000 | 180000 | 180000 | 900000 |  | CONS-8 | 1.5 | 120000
6617500
| Total |  | 1537500 | 1357500 |  | 1357500 |  | 1565000 | 1525000 | 1490000 | 1400000 | 7517500
[12 empty] | 1503500 |  | per year
| Total External Funding Needs |  | 1357500 |  |  |  |  | 1385000 | 1345000 | 1310000 | 1220000 | 6617500
[12 empty] | 1323500 |  | per year
Note on D10: In Ecotope's Contract
Note on D12: staff member: Contract covers 20 mths. 50% in 2009.

## Summary
Work Item | Approved 2010 Budget | Modified Approved Budget
End-Use Load Study - Phase 2a | 150000 | 3000 | -147000
Review RTF deemed measures, savings, and measure lives against others; document consistent methodology | 250000 | 235000 | -15000
Develop Simplified M&V protocols and/or calculators for non-deemable measures, including behavioral and O&M measures | 300000 | 235000 | -65000
Identify Measures and M&V Protocols that are applicable to small and/or rural utilities | 50000 | 50000
Provide Technical Support to the Ductless Heat Pump Evaluation. | 5000 | 5000
Support & Review Heat Pump Water Heater Research. | 5000 | 5000
Develop consistent methodology for assigning EUIs to commercial buildings | 10000 | 10000
Respond to NEET Recommendations for the RTF. | 5000 | 5000
Support Roof Top HVAC Work - Commercial Economizer Phase 3. | 37500 | 37500
Support Development of Savings Methodologies for Rooftop HVAC. | 5000 | 5000
Overhaul RTF Website. | 100000 | 10000 | -90000
PTR Support. | 15000 | 15000
Regional Conservation Progress Tracking | 10000 | 10000
Measure and Technology Reviews. | 200000 | 200000
IT M&V Protocol Review and Adoption | 20000 | 20000
Member & Corresponding Member Special Project Support. | 35000 | 35000
Member RTF Meetings. | 65000 | 65000
RTF Meetings. | 20000 | 20000
Contract Management. | 50000 | 50000
RTF Management. | 25000 | 25000
Council Staff | 180000 | 180000
Total Budget (not including Council Staff) | 1357500 | 1040500
Total Funding Commitments (not including Council Staff) | 1041341 | 1041341
Difference | -316159 | 841